## Sheet1
Reference to Proposal | User Story | Dev hours | Timeline (8h/week) | My own notes (at current understanding) | Maybes | Where to look in code | Notes to self (dev tasks) | Total hours
Internal | As a developer, I want a stable local Flask run/debug workflow so I can build features safely. | 12 | W1-W2 | Learn Flask basics (route, request, jsonify, session); run app end-to-end; fix current env loading; document "decisive" run steps; move hardcoded secrets out of code/bring to internet hostable state |  | Reuse run_web.py, app.py, pyproject.toml | Learn Flask basics (route, request, jsonify, session); run app end-to-end; fix current env loading; document "decisive" run steps; move hardcoded secrets out of code/bring to internet hostable state | 160
US-A1-01 | As a analyst, I want a clear disruption schema so natural language can be transformed into valid model input. | 8 | W3 | Create mapping between user language prompt and LLM output looks like a json schema, Impact Type, duration bounds, capacity bounds, location, lambda; create validation rules + defaults |  | Use disruption fields expected in model_input.py and CSV formats in Disruption_Profiles | Define JSON schema for service + demand disruptions; map NL terms to Impact Type, duration bounds, capacity bounds, location, lambda; create validation rules + defaults.
US-A1-02 | As a developer, I want a LLM API adapter so the app can make reliable LLM calls. | 10 | W4-W5 | Undersand existing SDKs, present options to, stakeholders. Add retry/error/tiemout handling , add prompt template for users. Maybe add versioning to the prompts. Verify a few basic calls |  | No current LLM module; extend from app.py pattern | Understand Gemini SDK/auth; create minimal ai_client module; add timeout/retry/error handling; add prompt template versioning; verify one basic call from Flask endpoint.
US-A1-03 | As a analyst, I want to describe a disruption in plain language and receive a structured scenario draft. | 14 | W6-W7 | current understanding:Build POST /api/ai/scenario/draft; pass prompt + schema, return JSON + confidence + missing fields; add frontend form + response preview. |  | Add new /api/ai/* routes in app.py, wire UI in index.html | Build POST /api/ai/scenario/draft; pass prompt + schema; return JSON + confidence + missing fields; add frontend form + response preview.
US-A1-04 | As a analyst, I want conversational refinement so I can iteratively improve a scenario. | 18 | W8-W10 | current understanding: Store conversation state in session; add refine endpoint; implement “what changed” diff in response | Add steering so that the model doesn't start halucinating | Session structure exists in LAHSOSession in app.py | Store conversation state in session; add refine endpoint; implement “what changed” diff in response; add guardrails against drift/hallucinated parameters.
US-A1-05 | As a analyst, I want automated parameter extraction with validation so scenarios are simulation-ready. | 16 | W11-W12 | Build extractor/normalizer; enforce numeric ranges and enum values; add missing-field clarification questions | Add missing-field clarification questions; add fallback manual edit form before run. (makes it way more useable) | Validation target comes from model_input.py and runtime behavior in simulation_module.py | Build extractor/normalizer; enforce numeric ranges and enum values; add missing-field clarification questions; add fallback manual edit form before run.
US-A1-06 | As a analyst, I want to save AI scenarios as LAHSO disruption files so I can run the engine unchanged. | 14 | W13-W14 | Implement CSV writer for generated profiles; store in Datasets/Disruption_Profiles/generated; add scenario selector in UI | Add timestamps to the files and maybe an ui for the user to see the different timestamp files of the same "scenario/request" | Reuse config paths in config.py and training/implementation config routes in app.py | Implement CSV writer for generated profiles; store in Datasets/Disruption_Profiles/generated; add scenario selector in UI; prevent overwrite collisions with timestamped filenames.
US-A2-01 | As an analyst, I want AI-generated scenarios to run through the resilience engine/q learning pipeline | 8 | W15 | Add only orchestration glue; run regression checks on baseline outputs; confirm no modification needed in simulation/optimization internals. |  | Engine already in model_implementation.py, model_train.py, optimization_module.py | Add only orchestration glue; run regression checks on baseline outputs; confirm no modification needed in simulation/optimization internals.
US-A4-01 | As a decision-maker, I want real scenario comparison charts (not demo data) to compare policy outcomes. | 18 | W16-W18 | Replace hardcoded values; dashboard; implement actual file upload/selection; api calls |  | Backend compare endpoint exists in app.py; logic in bar_chart_plot.py; frontend currently hardcoded in index.html | Replace hardcoded gpData/awData; implement actual file upload/selection; call /api/comparison/compare; bind returned deltas to charts.
US-A4-02 | As a decision-maker, I want recovery policy suggestions so I know which policy to apply after disruption. | 12 | W19-W20 | rule-based approach first; define scorign weights (cost, delay, udelivered, late); show to recommendations and explanation | maybe a ML model could be used, something that still keep explainability such as linear regression | Use metrics from global_variables.py and simulation outputs in csv_output | Build rule-based suggestion engine first (no extra ML); define scoring weights (cost, delay, undelivered, late departures); show top recommendation + rationale in dashboard.
US-A4-03 | As a decision-maker, I want intervention prioritization so I can act on highest-impact actions first. | 14 | W21-W22 | Add prioritized interventions table (action, expected impact, confidence); include filters and scenario switcher; add explanation text per item. |  | Use comparison deltas + output metrics from bar_chart_plot.py and global_variables.py | Add prioritized interventions table (action, expected impact, confidence); include filters and scenario switcher; add explanation text per item.
Internal | As a developer, I want end-to-end reliability checks and demo script so the proposal demo is defensible. | 16 | W23-W24 | Add Flask API tests for AI routes and compare route; add previous code tests; write demo script (happy path + fallback path); create troubleshooting checklist; prepare for handoff | I would spend more time here, to rewrite the other frontend code and delivered a user-ready product; as I would have already changed some of the code, it shouldn't be too much 8-12 more hours | Existing tests are placeholder in tests/test_main.py | Add Flask API tests for AI routes and compare route; add golden test scenarios; write demo script (happy path + fallback path); create troubleshooting checklist.

## Sheet2
Reference to Proposal | User Story | Dev hours | Timeline (8h/week) | My own notes (at current understanding) | Maybes
Internal | As a developer, I want a stable local Flask run/debug workflow so I can build features safely. | 12 | W1-W2 | Learn Flask basics (route, request, jsonify, session); run app end-to-end; fix current env loading; document "decisive" run steps; move hardcoded secrets out of code/bring to internet hostable state |  | Total hours
US-A1-01 | As a analyst, I want a clear disruption schema so natural language can be transformed into valid model input. | 8 | W3 | Create mapping between user language prompt and LLM output looks like a json schema, Impact Type, duration bounds, capacity bounds, location, lambda; create validation rules + defaults |  | 160
US-A1-02 | As a developer, I want a LLM API adapter so the app can make reliable LLM calls. | 10 | W4-W5 | Undersand existing SDKs, present options to, stakeholders. Add retry/error/tiemout handling , add prompt template for users. Maybe add versioning to the prompts. Verify a few basic calls
US-A1-03 | As a analyst, I want to describe a disruption in plain language and receive a structured scenario draft. | 14 | W6-W7 | current understanding:Build POST /api/ai/scenario/draft; pass prompt + schema, return JSON + confidence + missing fields; add frontend form + response preview.
US-A1-04 | As a analyst, I want conversational refinement so I can iteratively improve a scenario. | 18 | W8-W10 | current understanding: Store conversation state in session; add refine endpoint; implement “what changed” diff in response | Add steering so that the model doesn't start halucinating
US-A1-05 | As a analyst, I want automated parameter extraction with validation so scenarios are simulation-ready. | 16 | W11-W12 | Build extractor/normalizer; enforce numeric ranges and enum values; add missing-field clarification questions | Add missing-field clarification questions; add fallback manual edit form before run. (makes it way more useable)
US-A1-06 | As a analyst, I want to save AI scenarios as LAHSO disruption files so I can run the engine unchanged. | 14 | W13-W14 | Implement CSV writer for generated profiles; store in Datasets/Disruption_Profiles/generated; add scenario selector in UI | Add timestamps to the files and maybe an ui for the user to see the different timestamp files of the same "scenario/request"
US-A2-01 | As an analyst, I want AI-generated scenarios to run through the resilience engine/q learning pipeline | 8 | W15 | Add only orchestration glue; run regression checks on baseline outputs; confirm no modification needed in simulation/optimization internals.
US-A4-01 | As a decision-maker, I want real scenario comparison charts (not demo data) to compare policy outcomes. | 18 | W16-W18 | Replace hardcoded values; dashboard; implement actual file upload/selection; api calls
US-A4-02 | As a decision-maker, I want recovery policy suggestions so I know which policy to apply after disruption. | 12 | W19-W20 | rule-based approach first; define scorign weights (cost, delay, udelivered, late); show to recommendations and explanation | maybe a ML model could be used, something that still keep explainability such as linear regression
US-A4-03 | As a decision-maker, I want intervention prioritization so I can act on highest-impact actions first. | 14 | W21-W22 | Add prioritized interventions table (action, expected impact, confidence); include filters and scenario switcher; add explanation text per item.
Internal | As a developer, I want end-to-end reliability checks and demo script so the proposal demo is defensible. | 16 | W23-W24 | Add Flask API tests for AI routes and compare route; add previous code tests; write demo script (happy path + fallback path); create troubleshooting checklist; prepare for handoff | I would spend more time here, to rewrite the other frontend code and delivered a user-ready product; as I would have already changed some of the code, it shouldn't be too much 8-12 more hours